## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | More Than Meets The Eye
Group Member: | Wafaa Qaroma |  | Progress Classes: | Ahead
Group Member: | Timal Pathirana |  |  | On-track
Group Member: | Danny Van |  |  | Behind
Group Member: | Hoang Dang Khoa La |  |  | Way Behind
Tutor: | Dale Stanbrough
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Wafaa Qaroma | Timal Pathirana | Danny Van | Hoang Dang Khoa La
|  |  | Group Formed | Yes | Weekly Contribution | Designed ADT, linkedList, brainstroming developing patters, discussing testing approches. | Designed ADT, linkedList, brainstroming developing patters, discussing testing approches. | Designed ADT, linkedList, brainstroming developing patters, discussing testing approches. | Designed ADT, linkedList, brainstroming developing patters, discussing testing approches.
|  |  | MS Team created | Yes | Issues
|  |  | Git Repo created | Yes | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Wafaa Qaroma | Timal Pathirana | Danny Van | Hoang Dang Khoa La
|  |  | Choice of where to use linked list, vector & array | Design decisions need clarification | Weekly Contribution
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues
|  |  | Main menu |  | Other Notes
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | Behind
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Wafaa Qaroma | Timal Pathirana | Danny Van | Hoang Dang Khoa La
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution
|  |  | Initialisation of data strctures for new game | yes | Issues
|  |  | Write Tests Cases for common uses | only one UI test | Other Notes
|  |  | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic | behind
|  | Progress | Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Wafaa Qaroma | Timal Pathirana | Danny Van | Hoang Dang Khoa La
|  |  | Fully complete implementation and error free | ^D, | Weekly Contribution | Debugged Program | Debugged Program | Debugged Program | Debugged Program
|  |  | Full error checking of user prompt | mostly | Issues
|  |  | Automated placement of tiles at end of round, but no scoring | yes | Other Notes
|  |  | Final Tests | not enough
|  |  | Group Report Written | 1/2 way
|  | Progress | On-track